## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2.1.2026. | Hamza Nesimović | 1. Open Google Chrome and navigate to https://invictusshop.ba. 2. Navigate to the "Košulje" (Shirts) category. 3. Select any individual item to open the product page. 4. Observe the product actions area for a "Dodaj na listu želja" (Add to Wishlist) button. 5. Click the heart icon in the top right corner of the header to open the Wishlist window. Expected Results: Since a Wishlist page/window exists, each product should have a corresponding "Dodaj na listu želja" button or icon. Currently, this mechanism is missing, making it impossible for users to add items to their list.. Screenshots: https://prnt.sc/PKdMhkVIW_ja https://prnt.sc/2GRi-PExz0BK | [6 empty] | New |  |  |  |  | New
2 | 2.1.2026. | Hamza Nesimović | 1. Open Google Chrome and go to https://invictusshop.ba. 2. Navigate to the "Košulje" (Shirts) category. 3. Select any product that has a code in its name (e.g., "MK026") and only one dropdown menu for selection. 4. Click on the "Izaberite veličinu" dropdown and select any size. 5. Attempt to adjust the quantity. 6. Click the "Dodaj u košaricu" button. Expected Results: The quantity selector should remain visible and functional regardless of the product type. Currently, it disappears after size selection, causing only one (1) item to be added to the cart by default. Note: This issue specifically occurs on items that contain a code in the title (e.g., "MK", "MK026", or other numeric codes) and feature only a single dropdown selection. Products without these codes or those with multiple dropdown options do not seem to be affected by this bug. Screenshots: https://prnt.sc/aeSbwChy0Sqp https://prnt.sc/ibfFALwiVhFO | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 3.1.2026. | Tarik Drnda | 1. Open Firefox and navigate to https://invictusshop.ba. 2. Navigate to "Košulje" and select product "Muška košulja MK026". 3. Select a size and click "Dodaj u košaricu". 4. Verify that the cart drawer opens. 5. Remove the item from the cart by clicking the "delete" icon. 6. Close the cart by clicking the "X" button. 7. Observe the buttons on the product page. Expected Results: The "Vidi košaricu" button should be hidden once the cart is empty. Furthermore, given that permanent cart icons exist in the top-right and bottom-left corners, this additional button is redundant and creates UI clutter when no items are present. Screenshots: https://prnt.sc/OcwZKlikhjIi https://prnt.sc/LQw6o3d6bbR6 | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 6.1.2026. | Rijad Alihodžić | 1. Open Firefox and navigate to https://temu.com. 2. Log in with a valid user account. 3. Inside the application navigate to temu homepage. 4. Select any product and add a Quantity of 1 of that item into the shopping cart using the Add to cart button. 5. Click on 'Checkout' to proceed to the checkout page. 6.Navigate to the Shipping address section. 7.Enter the following SQL injection string in the "Street name and House number" field ';DROP TABLE orders; -- 8.Fill in the remaining fields with valid data (city, country, Postal code, phone number, first name, last name). 9.Click Save to proceed. 10.Observe that the address is accepted without any validation error. Expected Results: The system should validate the street address field and reject input containing SQL injection patterns, special character combinations (such as '; --), or suspicious strings. An appropriate error message should be displayed, such as "Invalid characters in address field" or "Please enter a valid street address." Input sanitization should occur on both frontend and backend to prevent potential SQL injection attacks. Screenshots: https://prnt.sc/bZlueuXTO5eE https://prnt.sc/R9BmtrwW9VDs | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 6.1.2026. | Rijad Alihodžić | 1. Open Firefox and navigate to https://temu.com. 2. Log in with a valid user account. 3. Inside the application navigate to temu homepage. 4. Select any product and add a Quantity of 1 of that item into the shopping cart using the Add to cart button. 5. Click on 'Checkout' to proceed to the checkout page. 6.Enter valid shipping address information. 7.Select Credit/Debit Card as the payment method 8.Verify that the order confirmation page is displayed with an order number. 9.Note the order number for reference. 10.Immediately navigate to My Orders section on the home page in the app (within 1 minute of order placement) 11.Locate the newly created order and click "Return/Refund" to refund the money and cancel the order. 12.Complete the cancellation/refund process. 13.Check the registered email inbox and all of the folders for order mails from temu. 14.Observe that you did not receive any email neither for the confirmation of the order or cancellation/refund. Expected Results: An order confirmation email should be sent immediately after successful payment, containing order number, items purchased, shipping address, and estimated delivery date. A separate refund/cancellation confirmation email should be sent after the refund is processed, containing refund amount, original order number, and estimated refund processing time. Both emails should arrive regardless of how quickly the order was cancelled after placement. Screenshots: https://prnt.sc/ReAf9yy1YFxi https://prnt.sc/zODQXBSqhAaG https://prnt.sc/EBsJs1JDDwS8 https://prnt.sc/pnZFXH1kj4Fd | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | [16 empty] | Closing | Development
7 | [17 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).